## Sheet2
MITS 2.0 - SDS UPDATE
MODULE | ITEMS
| ENTITY RELATIONSHIP DIAGRAM (ERD) | PIC/ TARGET DATE | TABLES DESCRIPTION | PIC/ TARGET DATE | DATA ELEMENT DICTIONARY | PIC/ TARGET DATE
ADMINISTRATOR | 41/41 - DONE | FAIZ | 0/10 - NO PROGRESS | AMIR/ 15 MARCH | 9/41 - IN PROGRESS | AMIR/ 16 MARCH
INTERVENTION MODULE | 54/54 - DONE | FAIZ | DONE | AMIR | 0/54 - NO PROGRESS | AMIR/ 16 MARCH
PATIENT MODULE | 5/5 - DONE | FAIZ | DONE | AMIR | 5/5 - DONE | AMIR
SHHARP MODULE | 11/11 - DONE | FAIZ | DONE | NURUL | 9/11 - IN PROGRESS | FAIZ/ 16 MARCH
VON MODULE | 10/10 - DONE | FAIZ | DONE | NURUL | 0/10 - NO PROGRESS | FAIZ/ 15 MARCH